# QOrium CEO Action Cards

Purpose: Every Part C task has one card. Cards are released in dependency order. Open card = act now. Queued card = wait for upstream. Format: What · Where · When · Why · How (5 steps max) · Evidence-back to CTO How to use: Pick the topmost OPEN card. Do it. Send the Evidence-back to CTO Office. Next card releases.

## OPEN — Act Now

### CC-01 — Open the QOrium ringfenced bank account or budget line

One-sentence what: Decide whether QOrium gets its own bank account OR a tagged sub-budget under Talpro Universe; create whichever you choose.

Where: 🏦 Your banking app or CFO conversation

When: Day 0–3 (this week)

Why: Without a ringfenced account, the ₹50L envelope is conceptual — every other Phase 0 task depends on this being real money in a real account. Blocks 12 downstream tasks.

How: 1. Decide: separate QOrium account OR Talpro Universe sub-budget tagged “QORIUM”? 2. If separate account: open via your bank’s online portal (HDFC/ICICI/Axis support same-day for existing customers) 3. If sub-budget: ask CFO/Finance to tag a sub-account “QORIUM” with ₹50L allocated 4. Capture the account number / budget reference number 5. Send back to CTO Office (one-line message)

Evidence-back to CTO: > “✅ CC-01 done. Account opened/tagged: [account number or sub-budget ref]. Available balance: ₹50L. Date: [DD-MM].”

After this: CC-04 (BP-01 domain registration) and BP-04 (Cloudflare R2 bucket) auto-release with billing tied to this account.

### CC-02 — Engage IP counsel for trademark + MSA + DPA

One-sentence what: Engage an IP/commercial lawyer to handle QOrium’s trademark filings (India + US) and contract templates (MSA + DPA).

Where: 📞 Phone or 📧 email — your existing legal counsel relationship if any, or new

When: Day 0–7

Why: Trademark must be filed before public launch (protects “QOrium” + SKU names ReadyBank/JD-Forge/Stack-Vault). MSA + DPA are blockers for ANY enterprise contract — Bosch GCC will not sign without them.

How: 1. If you have existing IP counsel for Talpro Universe: extend their engagement to cover QOrium 2. If not: pick a Bengaluru/Mumbai IP firm with software trademark experience (Class 9 + 42) 3. Send a one-paragraph engagement email — say “ask CTO for draft” if you want me to write it 4. Sign their engagement letter when sent 5. Send back to CTO Office

Evidence-back to CTO: > “✅ CC-02 done. IP counsel engaged. Firm: [name]. Engagement letter signed [date]. Estimated trademark filing ETA: [date].”

After this: CC-08 (trademark filing) and the legal-review path for MSA + DPA auto-release.

### CC-03 — Brief Talpro India Delivery Head on Customer Zero scope

One-sentence what: 15-minute call with the Talpro India Delivery Head explaining QOrium Customer Zero scope (top 5 roles, 100+ candidates by M3, weekly feedback loop).

Where: 📱 WhatsApp call or in-person

When: Day 0–3

Why: Customer Zero is non-negotiable per Constitution SO-1. Without Delivery Head buy-in, Talpro candidate flow doesn’t switch to QOrium and you lose the Day-1 reference asset. Blocks 4 downstream tasks (D2, D4, D5, plus the Bosch sample-pack pre-work).

How: 1. Schedule 15-min call with Delivery Head this week 2. Walk through: “QOrium will replace our default assessment platform for top 5 roles starting Month 1” 3. Get their list of top 5 roles (typical: Senior Java, React, SQL/Data, DevOps, Salesforce) 4. Get verbal commitment to weekly feedback channel (Slack #qorium-customer-zero or equivalent) 5. Send back to CTO Office

Evidence-back to CTO: > “✅ CC-03 done. Talpro Delivery Head [name] briefed [date]. Top 5 roles: [list]. Weekly feedback channel: [Slack channel name or commitment].”

After this: D2 (CTO collects Talpro JDs), D4 (feedback channel setup), D5 (initial 100-question seed batch can begin) all auto-progress.

## QUEUED — Will Release When Upstream Clears

These are Part C cards that aren’t ready yet. They release as upstream tasks complete. You don’t need to read these yet — I’ll re-publish each one when it’s your turn, with full instructions.

### CC-04 — Domain registration via Hostinger

One-sentence what: Register qorium.io and qorium.in domains; enable DNS + email forwarding.

Where: 🌐 Hostinger (or GoDaddy/Namecheap if you prefer)

When: Day 3–5 (once CC-01 complete and billing account confirmed)

Why: Domains required before public launch, email signups, API documentation at custom domain. Blocks: CC-09 (JD postings with QOrium email), website launch, email addresses for team.

How: 1. Visit Hostinger.com (or equivalent); log in / create account 2. Search qorium.io — purchase 3-year term (₹700–₹1,000 total); use QOrium ringfenced account for billing 3. Search qorium.in — purchase 3-year term (₹700–₹1,000 total) 4. Enable DNS management (Hostinger default) 5. Send back to CTO Office with domain registrar login (share securely via Notion or KeePass)

Evidence-back to CTO: > “✅ CC-04 done. Domains registered: qorium.io, qorium.in (3-year terms, auto-renewal enabled). DNS access granted via [Hostinger account / shared creds]. Registrar login: [shared securely].”

After this: Website domain ready for CTO to point DNS. Email setup begins (postmaster@qorium.io).

### CC-05 — GitHub organization creation + first repo

One-sentence what: Create QOrium GitHub org, seed first repo with branch protection and core documentation.

Where: 🔗 GitHub.com (new org creation)

When: Day 3–5 (independent; no prerequisite)

Why: Code repository + documentation home required before content pipeline development begins. Blocks: D6 (content pipeline code), D8 (API SDK), engineering team GitHub onboarding.

How: 1. Go to GitHub.com; log in as personal account (or create if needed) 2. Create new organization: name = “QOrium” (or “qorium-io” if taken); description = “Question-Bank-as-a-Service” 3. Create first repository: name = “qorium-core”; visibility = Private; initialize with README 4. Enable branch protection on main: require PR review (1+ approver), dismiss stale reviews, require status checks 5. Share org + repo invite link with CTO

Evidence-back to CTO: > “✅ CC-05 done. GitHub org created: github.com/QOrium. First repo: qorium-core (private, branch protection enabled on main). CTO/Senior Engineer invites pending.”

After this: Senior Engineer and SME Lead GitHub access provisioned; they can begin content pipeline code development.

### CC-06 — AI API keys procurement + budget alerts

One-sentence what: Set up API keys for Anthropic Claude, OpenAI GPT-4, Google Gemini; configure budget alerts and usage monitoring.

Where: 🔐 Anthropic, OpenAI, Google Cloud consoles

When: Day 3–5 (independent; small ₹10K–₹20K from envelope)

Why: AI APIs required for content generation (GPT-4 drafting), self-critique, quality checks, JD-Forge workflows. Budget alerts prevent overspend.

How: 1. Anthropic console (console.anthropic.com): create API key; set monthly budget alert ($500–$1,000) 2. OpenAI console (platform.openai.com): create API key; configure GPT-4 usage limits (set hard limit ₹50K/month) 3. Google Cloud console: enable Gemini API; create API key; set billing alert 4. Store keys in secure password manager (Notion, KeePass, or 1Password shared team vault) 5. Share key access with CTO and Senior Engineer

Evidence-back to CTO: > “✅ CC-06 done. API keys provisioned: Anthropic (Claude), OpenAI (GPT-4), Google (Gemini). Monthly budgets set: $500 (Anthropic), $1,000 (OpenAI), $200 (Google). Usage dashboards configured. Keys shared securely with CTO.”

After this: Content pipeline can begin AI-assisted drafting in Week 1 Month 1.

### CC-07 — Send Bosch GCC warm-intro email

One-sentence what: Personalize and send warm-intro email to Bosch Bengaluru TA Head, positioning QOrium Stack-Vault.

Where: 📧 Your email (CEO account)

When: Day 7–10 (after CC-01, CC-03, E1 complete; Bosch research ready)

Why: Bosch is marquee customer target (Month 4–5 close). Warm intro from you (CEO) unlocks meetings otherwise impossible. Blocks: AE Enterprise Day 30 sample pack delivery goal.

How: 1. Gather from E1 (Bosch research): TA Head name, email, hiring volume (hires/year), current platform 2. Draft: personalize E1-Bosch template or write from scratch (CTO offers template if requested) 3. Attach: Bosch-variant one-pager (from DOC 2 design spec) + brief Stack-Vault overview 4. Send: same day; copy CEO + AE Enterprise; request 15-min intro call within 2 weeks 5. Log in HubSpot: create Bosch company + contact record; mark deal “Outreach”

Evidence-back to CTO: > “✅ CC-07 done. Warm-intro email sent to Bosch TA Head [name] on [date]. Copy: [email], AE Enterprise [name]. One-pager attached. Follow-up call requested by [target date].”

After this: AE Enterprise activates Bosch in HubSpot pipeline; sample pack pre-work begins (coordinate with Senior Engineer).

### CC-08 — Trademark filing kick-off with counsel

One-sentence what: Provide IP counsel with trademark details; counsel files India + US trademarks for “QOrium” + SKU names (ReadyBank, Stack-Vault, JD-Forge).

Where: 📧 Email to IP counsel (or in-person meeting if Bengaluru-based)

When: Day 10–14 (after CC-02 engagement letter signed)

Why: Trademark protection must complete before public launch (logo assets live, website public, customer contracts signed). Prevents competitor squatting on names. Blocks: public launch, customer contracts, investor decks.

How: 1. Gather: trademark details from Brand Spec (DOC 1): QOrium wordmark + logo files, color codes, 3 SKU names 2. Prepare 2-paragraph brief: “File ‘QOrium’ (Class 9 software, 42 services). File ‘ReadyBank,’ ‘Stack-Vault,’ ‘JD-Forge’ (Class 42). India + US. Timeline: 90 days.” 3. Email to IP counsel; attach logo PDF + brief 4. Call counsel (30 min): confirm filing strategy, timeline, costs, next steps 5. Send back to CTO

Evidence-back to CTO: > “✅ CC-08 done. IP counsel [firm name] filing initiated on [date]. Trademarks: QOrium (wordmark), ReadyBank, Stack-Vault, JD-Forge (all Classes 9 + 42, India + US). Expected approval date: [date]. Cost: [₹ amount]. Next action: IP counsel submits applications by [date].”

After this: Trademark filings progress in parallel; expected approval Month 3–4. Customer contracts can proceed pending final trademark confirmation.

### CC-09 — Senior Engineer + SME Content Lead JD posting

One-sentence what: Post 2 job descriptions (Senior Engineer, SME Content Lead) on LinkedIn, Naukri, Talpro alumni network.

Where: 🔗 LinkedIn, Naukri, internal alumni Slack/WhatsApp groups

When: Day 14–21 (after C1 + C2 JD documents complete and finalized)

Why: Engineering hires required by Month 3 to begin Customer Zero delivery and content pipeline setup. Typical hiring cycle 4–8 weeks.

How: 1. Finalize JDs: Senior Engineer JD (from CTO deliverable C1), SME Content Lead JD (from C2) 2. Create LinkedIn job posts: copy title, description, apply link (use Talpro ATS or direct email) 3. Post to Naukri: similar; set application deadline 30 days 4. Share in Talpro alumni Slack/groups: tag former team members, offer referral bounty if desired 5. Monitor: track applications weekly; share short-list with CEO by Day 35

Evidence-back to CTO: > “✅ CC-09 done. JDs posted on [date]. LinkedIn: [job post link]. Naukri: [job post link]. Alumni groups: [Slack channels notified]. Application deadline: [date]. Expected first interviews: Week 3–4.”

After this: Hiring process begins; interviews + offers target Month 2 (CC-11).

### CC-10 — First Bosch GCC discovery call

One-sentence what: Joint discovery call with Bosch TA Head (you + CTO + AE Enterprise); validate pain, understand stack, propose sample pack.

Where: 📞 Zoom (or in-person if Bengaluru site visit feasible)

When: Month 1, Week 2–3 (after Bosch warm-intro response received; usually Week 2–3 response time)

Why: First marquee prospect validation. Success of this call informs sample pack scope, AE Enterprise confidence, and Bosch deal timeline. Sets tone for enterprise motion.

How: 1. Prepare (you + CTO + AE Enterprise): 30-min internal prep call 24 hours before - Review Bosch-specific research (from E2) - Define discovery call agenda: pain, stack, hiring volume, procurement timeline, decision authority - Role split: you (positioning), CTO (tech architecture Q&A), AE (discovery notes) 2. Bosch discovery call (45 min): ask 5–6 probing questions; listen for pain; quantify assessment spend 3. Close: “If we delivered a 50-question sample on [top role] by [date], would your engineering team review?” 4. Post-call (1 hour): AE Enterprise + you debrief; CTO notes engineering requirements 5. Within 24 hours: AE Enterprise sends recap email + sample pack timeline to Bosch

Evidence-back to CTO: > “✅ CC-10 done. Bosch GCC discovery call held [date]. Attendees: CEO, CTO, AE Enterprise, Bosch TA Head [name] + [# other attendees]. Key findings: hiring volume [#/year], current platform [Mettl/HackerRank], pain [fraud/cost/staleness], decision authority [TA Head + CFO], sample pack request: YES, timeline [2 weeks]. Next step: AE Enterprise delivers sample pack by [date].”

After this: Senior Engineer coordinates sample pack authoring (50 questions, top role); AE Enterprise owns delivery + review coordination.

### CC-11 — Senior Engineer + SME Content Lead interviews + offer letters

One-sentence what: Conduct final-round interviews with shortlisted candidates; extend and sign offer letters; confirm start dates.

Where: 📱 Zoom (or in-person)

When: Month 2 (Week 1–2; typically 6–8 weeks post-posting)

Why: Engineering team must onboard by Month 3 to deliver Customer Zero content and build content pipeline. Delays here delay all downstream delivery.

How: 1. Review shortlist (typically 3–5 candidates per role): filter to top 2 2. Final-round interviews (60 min each): you + CTO; assess technical depth, culture fit, customer success mindset 3. Debrief with CTO: select offers 4. Prepare offer letters: base salary, equity, start date (target Month 3 start, ~Week 1) 5. Extend offers: call first, then send formal email with offer letter PDF 6. Upon acceptance: coordinate onboarding (equipment, GitHub access, first-week schedule)

Evidence-back to CTO: > “✅ CC-11 done. Interviews completed Week [W]. Senior Engineer offer: [name, salary, equity, start date]. SME Content Lead offer: [name, salary, equity, start date]. Both accepted [dates]. Onboarding scheduled: [Week of Month 3].”

After this: Engineering team onboarding begins Week 1 Month 3; they begin content pipeline setup + Customer Zero prep.

### CC-12 — AE Enterprise + BD Platforms interviews + offer letters

One-sentence what: Conduct final-round interviews with shortlisted AE and BD sales leads; extend offer letters; confirm Month 3 start dates.

Where: 📱 Zoom (or in-person)

When: Month 2 (Week 2–4; overlaps with engineering interviews)

Why: Sales team must onboard by Month 3 to begin Day 1 pipeline building and first prospect outreach. Delays cascade to enterprise motion timeline.

How: 1. Review shortlist: typically 3–5 per role; filter to top 2 per role (AE + BD) 2. Final-round interviews (90 min each): you + advisor (mentor from Talpro portfolio); assess sales motion understanding, market knowledge, founder mentorship fit 3. Optional: candidate pitches QOrium to mock prospect (see JD roleplay evaluation) 4. Debrief: select offers 5. Prepare offer letters: base salary, variable comp structure, equity, start date (target Month 3 Week 1) 6. Extend offers: call first, then send formal email + offer letter 7. Upon acceptance: coordinate onboarding (equipment, HubSpot access, Week 1 schedule)

Evidence-back to CTO: > “✅ CC-12 done. Interviews completed Week [W]. AE Enterprise offer: [name, base, OTE, equity, start date]. BD Platforms offer: [name, base, OTE, equity, start date]. Both accepted [dates]. Onboarding scheduled: [Week of Month 3].”

After this: Sales team onboarding Week 1 Month 3; they begin prospect list building + outreach (Day 30 milestones per DOC 4).

## DONE

(Cards move here as you complete them and send evidence-back. Empty for now.)

## CARD STATUS LEGEND

- ⏳ OPEN — released, ready for you to act

- 📦 QUEUED — released but awaiting upstream

- ✅ DONE — completed; evidence captured

- ⏸ PAUSED — explicitly paused

- 🚫 CANCELED — no longer relevant; documented reason

## OPERATING PROMISE (CARD-LEVEL)

- Cards are short — 5 steps max each.

- One open card at a time is the goal — but Day 0 has 3 in parallel because they’re independent.

- Evidence-back format is fixed — copy the template; fill in the brackets. That’s it.

- No card released until prerequisites are met — you’ll never see a card you can’t act on.

- Cards are revised, not abandoned — if a card stalls, I revise it; I don’t drop it silently.

## QUICK REFERENCE — Today’s Three Open Cards (Day 0)

| Card | Task (one-line) | Where | Time |
| --- | --- | --- | --- |
| CC-01 | Open QOrium ringfenced account / sub-budget | Banking app / CFO | 10 min |
| CC-02 | Engage IP counsel | Phone/email | 15 min |
| CC-03 | Brief Talpro Delivery Head | WhatsApp call | 15 min |

Total CEO time today: ~40 minutes. Unblocks ~12 downstream tasks.

## QUICK REFERENCE — Days 3–30 Queued Tasks (Card Release Timeline)

| Card | Task (one-line) | When | Prereq | Est. Time |
| --- | --- | --- | --- | --- |
| CC-04 | Domain registration (qorium.io, qorium.in) | Day 3–5 | CC-01 | 15 min |
| CC-05 | GitHub org + first repo setup | Day 3–5 | — (independent) | 15 min |
| CC-06 | AI API keys (Anthropic, OpenAI, Gemini) | Day 3–5 | — (independent) | 15 min |
| CC-07 | Send Bosch warm-intro email | Day 7–10 | CC-01, CC-03, E1 | 10 min |
| CC-08 | Trademark filing with counsel | Day 10–14 | CC-02 | 30 min (spread over 1–2 weeks) |
| CC-09 | Post Senior Engineer + SME Lead JDs | Day 14–21 | C1, C2 finalized | 20 min |
| CC-10 | First Bosch discovery call | Month 1, W2–3 | CC-07 response | 45 min call + 30 min prep |
| CC-11 | SE + SME Lead interviews + offers | Month 2, W1–2 | CC-09 applications | 60 min/candidate × 2 roles |
| CC-12 | AE Enterprise + BD interviews + offers | Month 2, W2–4 | Job postings live | 90 min/candidate × 2 roles |

Total CEO time Days 3–30: ~2–3 hours (spread across 4 weeks). Remaining cards (CC-04, CC-05, CC-06) are brief; CC-08 is async with counsel.

End of CEO Action Cards. Open cards above. Send evidence-back when done.