# QOrium — SME Contractor Sourcing Plan v1.0

Author: CTO + CEO, Talpro Universe
Audience: SME Content Lead, Content Operations Manager (hire #2, #7), contractor managers, procurement
Date: May 2, 2026
Status: Operating-grade sourcing roadmap; channels ranked by expected CPA
Related docs: Blueprint v1.1 · CTO Architecture v1.0 · C7 Compensation Philosophy

## 1. Goal + Volume Targets

QOrium’s content engine depends on a scaled, distributed network of Subject Matter Expert (SME) contractors to validate AI-authored questions. The network scales in three waves:

- Wave 1 (M0–M3): 30 SME contractors across 8–10 core domains

- Wave 2 (M3–M6): 100 SME contractors; add India-stack domain depth (SAP, Oracle, Salesforce, BFSI)

- Wave 3 (M6–M12): 250 SME contractors; add aptitude + psychometric authoring

By end of M12, the SME network is self-sustaining — high-quality contractors refer new contractors, quality bar is codified in rubrics, and the SME Content Lead can manage the network without CEO/CTO hands-on oversight.

## 2. Domain Coverage Targets (mapped to Blueprint Phase Gates)

### Wave 1 (M0–M3): Core Tech Stack

Target: 30 contractors, 8–10 contractors per major domain.

| Domain | Target # | Why | Key Roles/Skills |
| --- | --- | --- | --- |
| Senior Java | 10 | Backend volume; Java Spring is #1 tech stack in BFSI + enterprise | Spring, Transactions, Microservices, JVM tuning |
| React/JavaScript | 8 | Frontend core; JS/TS across full stack | React hooks, state mgmt, async patterns, performance |
| SQL/Data | 8 | Highest-demand skill across assessment platforms | Complex queries, optimization, data modeling |
| DevOps/SRE | 6 | Growing demand from GCCs; infrastructure as code | Kubernetes, Terraform, CI/CD, observability |
| Salesforce | 6 | GCC + enterprise focus; high-value assessments | Apex, SOQL, data model, Sales Cloud, Service Cloud |
| Python | 6 | Data + AI/ML roles; growing in startups | Pandas, Flask, async, testing patterns |

Total Wave 1: 44 contractors (we’ll aim for 30 committed + 14 overflow / spill).

### Wave 2 (M3–M6): India-Stack + Backend Depth

Add domains tied to Blueprint §3.5 Wave 2 content goals.

| Domain | Target # | Why | Key Roles/Skills |
| --- | --- | --- | --- |
| SAP ABAP | 12 | Largest demand from GCCs (Bosch, Siemens, JPMC India); wave-specific priority | ABAP OO, webdynpro, BAPIs, data dictionary |
| Oracle HCM | 10 | HR + IT services hiring; enterprise focus | HCM Data Model, Fusion API, custom extensions |
| Finacle/Flexcube | 8 | BFSI core systems; niche expertise | Lending/deposits workflows, batch processing |
| Embedded Automotive | 6 | Bosch + automotive GCCs; specialized | AUTOSAR, MISRA-C, CAN protocols, ASPICE |
| Salesforce (CPQ/Service) | 6 | Expand beyond admin/dev basics | Salesforce CPQ, Service Cloud depth, flow builder |
| Node.js/Express | 6 | Backend JavaScript stack growing; gaps in Wave 1 coverage | Async, middleware, scaling patterns |
| Aptitude/Psych authors (contractor → FTE path) | 4 | Early hire #8 (I/O Psych FTE) trains these on numerical/verbal/abstract reasoning question authoring | Numerical reasoning, verbal, abstract, SJT design |

Wave 2 total: 52 new contractors (~82 cumulative by M6).

### Wave 3 (M6–M12): Psychometric + Advanced Formats

Tie to Blueprint §3.5 Wave 3 & 4 content goals.

| Domain | Target # | Why | Key Roles/Skills |
| --- | --- | --- | --- |
| Aptitude/Numerical/Verbal | 20 | Scale SJT + cognitive ability authoring; hire #8 (I/O Psych) leads training | Numerical reasoning, verbal logic, abstract reasoning, SJT scenarios |
| AI Prompt Evaluation | 15 | Wave 4 formats; authors expert at evaluating LLM output quality for AI-era assessment questions | ChatGPT/Claude prompt design, evaluation rubrics |
| Case Study / Scenario | 10 | Higher-complexity format; business context authoring | Case study design, business simulation scenarios |
| AI-Collaboration Assessment | 8 | Specialized format; authors who’ve worked on collaborative AI evaluation | AI pair-programming, co-pilot evaluation |

Wave 3 total: 53 new contractors (~135 cumulative by M12).

Final network by M12: 250+ contractors covering 20+ tech stacks + aptitude + psychometric domains.

## 3. Sourcing Channels (ranked by expected CPA)

All channels are ranked by Customer Acquisition Cost (CPA) — the effective cost to vet, onboard, and activate a contractor. CPA includes: time (in ₹/hour equivalent), success rate (% who complete vetting), and downstream utilization (% who complete ≥ 5 questions before churn).

### Channel 1: Talpro India Alumni Network (Lowest CPA ~₹2,000–5,000)

Activation: CEO + SME Content Lead directly reach out to ex-Talpro India staff (recruiters, trainers, engineers, QA specialists) who’ve moved to staffing firms, coaching institutes, or freelance.

Volume target: 40% of final network (100 contractors by M12) sourced this way.

Why: Warm relationship, brand trust, cultural fit, low friction. Talpro India network is ~500 people across India (Bengaluru, Hyderabad, Pune, NCR, Chennai); estimated 200–250 are senior enough for SME work.

Outreach: Personal WhatsApp → 15-min Zoom conversation (pitch is: “QOrium pays ₹500–₹2,000 per question; you review AI-drafted questions, we pay on approval; 5–10 hours/month to start, can grow”). No formal application.

Vetting: CV + 1 sample question authored in sandbox + 30-min call + first pilot batch (5 questions) at ₹2,500/batch.

Timeline: M1 onward; should land 10 by M2, 30 by M4.

### Channel 2: NIT/IIT Alumni Network (CPA ~₹3,000–8,000)

Activation: Bhaskar’s personal network (IIT Bombay batch of 2001–2003) + LinkedIn alumni group + WhatsApp groups.

Volume target: 25% of network (62 contractors by M12).

Why: Tier-1 engineers; high quality bar; India-dense alumni network.

Outreach: LinkedIn message to “NIT/IIT alums” with keyword search: senior engineers who’ve gone independent or are coaching/content creators. Offer referral bonus: ₹15,000 per successful contractor (see Channel 6 referral bonus).

Vetting: Same as Talpro alumni.

Timeline: M2 onward; 5 by M3, 20 by M6.

### Channel 3: Topmate / Mentor.com / GrowthSchool (CPA ~₹4,000–12,000)

Activation: Scout platforms where ex-engineers monetize as mentors/coaches.

Volume target: 15% of network (38 contractors by M12).

Why: Mentors are already thinking of themselves as educators; transition to SME authoring is natural. Platform has vetting, reviews, payment infra built-in.

Outreach: Direct message on Topmate to mentors offering “Java Spring” / “React” / “SQL” mentorships in India. Pitch: higher-per-hour rate (₹3,000–5,000 per question vs ₹100–200/hour mentoring).

Vetting: Topmate review history = pre-vetting; still do sample question + 30-min call.

Timeline: M3 onward; steady stream.

### Channel 4: Hashnode / Dev.to / Medium Tech-Blogger Outreach (CPA ~₹3,000–8,000)

Activation: Scout technical bloggers on Hashnode, Dev.to, Medium who write tutorials, deep-dives on niche topics (ABAP, Finacle, SAP HCM, embedded systems).

Volume target: 10% of network (25 contractors by M12); Wave 2 dominant (India-stack experts).

Why: These bloggers have already written 10–20 technical articles; proof of expertise + writing clarity.

Outreach: Email or Twitter DM: “Your article on [SAP ABAP transaction handling] was excellent. QOrium is building a question bank; we pay ₹1,500–₹3,000 per validated question. Interested?” Include: sample question, timeframe (5–10 hrs/month to start), and link to apply.

Vetting: Portfolio (blog posts) = pre-vetting; sample question + call.

Timeline: M3 onward; expect 1–2/week inbound.

### Channel 5: LinkedIn Boolean Search + CTO-Office Cold Templates (CPA ~₹6,000–15,000)

Activation: SME Content Lead (or future Content Ops Manager) runs LinkedIn searches with Boolean strings. Templates are crafted by CTO Office.

Example search strings:

"Senior Engineer" AND (Java OR Spring) AND India AND (independent OR freelance OR "looking for")
"Staff Engineer" AND "Data Engineer" AND ("Bengaluru" OR "Hyderabad") AND -"hiring managers"
(ABAP OR "SAP ABAP") AND (Bangalore OR Pune OR Hyderabad) AND (5+ OR 6+ OR 7+ OR 8+) years

Volume target: 7–10% of network (20 contractors by M12).

Why: Long tail; low volume but high quality (passive candidates + strong passive.

Outreach: Templated InMail or LinkedIn message (CTO writes 3 variants; Content Lead personalizes the first line and sends):

Hi [Name], saw your background in [Domain]. QOrium is building the world’s question bank for hiring — we pair AI drafting with SME validation. If you’re open to 5–10 hours/month earning ₹500–₹2K per question, let’s chat. [Link to apply].

Vetting: Same as above.

Timeline: M4 onward; ongoing sourcing.

### Channel 6: Referrals from First 5–10 SME Hires (CPA ~₹1,500; includes bonus)

Activation: Once 5–10 SMEs are active and completing questions, offer referral bonus: ₹15,000 per successful referral (contractor completes vetting + 5 pilot questions).

Volume target: 20–25% of network (50–62 contractors by M12); increasing percentage as network grows.

Why: Best predictor of quality (SME referral = implicit quality endorsement). Self-sustaining virality.

Outreach: Email: “Refer a senior [Java/React/ABAP] engineer. When they complete vetting + 5 questions, you both get ₹15K.” Include referral link, FAQ, and timeline.

Timeline: M3 onward; network effect should accelerate by M6.

## 4. Vetting Protocol (standardized, repeatable)

Every contractor — regardless of channel — passes the same gate:

### Gate 1: CV Review (async; 24 hours)

Action: SME Content Lead or freelance reviewer checks CV for: - 5+ years experience in the target domain - Evidence of technical depth (job titles, certifications, portfolio links) - India-based or remote-ready (timezone compatible with IST)

Pass/fail: Reject if not meeting 5+ years or unclear domain depth. Otherwise, advance.

### Gate 2: Sample Question Authored in Sandbox (async; 5–7 days)

Action: Contractor given sandbox access (Google Doc or Notion template) + 2 reference questions from QOrium’s library. Task: author ONE question in the target domain, same format + rigor.

Evaluation rubric (100 points): - Technical correctness (30 pts): Answer is accurate; test cases cover edge cases - Clarity + ambiguity (25 pts): No reasonable misinterpretation of the question; distractors are plausible - Bias + edge cases (20 pts): No gendered/regional/cultural assumptions; covers boundary conditions - Formatting (15 pts): Follows template; proper syntax/structure - Leak risk (10 pts): Doesn’t directly copy public resources (GeeksforGeeks, LeetCode, etc.)

Pass/fail threshold: 75+ pts → advance to call. <75 → send feedback (“resubmit in 1 week if interested”) or reject.

### Gate 3: 30-min Video Call (sync; schedule within 2 weeks)

Action: SME Content Lead or I/O Psych contractor does structured interview: - Confirm domain expertise (ask 2–3 hard technical questions specific to their claimed stack) - Assess communication + teaching ability (ask: “Walk me through your answer to the sample question”) - Confirm availability (5–10 hours/month to start; willing to grow?) - Set expectations (payment model, turnaround, quality bar, NDA)

Pass/fail: Advance if confident they can handle 5–10 questions/month without hand-holding. Veto if unclear on quality or communication.

### Gate 4: First Paid Pilot Batch (5–10 questions; ₹2,500–₹5,000 depending on complexity)

Action: Contractor author + SME review 5–10 questions. Pay for the batch if 4/5+ pass internal quality gate (AI self-critique + spot-check by I/O Psych or SME Lead).

Turnaround: Contractor has 2 weeks to submit; 1 week for review + feedback + payment.

Pass/fail: If 4/5+ pass → contractor is “certified” and can take ongoing batches. If <4/5 pass → offer one resubmit, then sunset if second attempt fails.

Timeline: M1 start → should have 30 “certified” contractors by M3.

## 5. SME Commercials (per-question + reviewer pool bonus)

### Per-Question Rate (by complexity + domain)

| Format | Complexity | Typical Rate (₹) | Examples |
| --- | --- | --- | --- |
| MCQ | Easy | 500 | Beginner-level Java, SQL, general concepts |
| MCQ | Medium | 750 | Mid-level design questions, edge cases |
| MCQ | Hard | 1,000 | Expert-level system design, rare patterns |
| Coding (function) | Easy | 1,200 | Simple DSA, basic SQL queries |
| Coding (function) | Medium | 1,500 | LeetCode-style medium, real-world scenarios |
| Coding (function) | Hard | 2,000 | Hard DSA, complex system design, real-codebase context |
| SJT / Scenario | Medium | 1,200 | Behavioral, scenario-based (not auto-graded) |
| Case Study | Hard | 2,000 | Business case, multi-step analysis |
| Real-codebase task | Hard | 3,000+ | DevSkiller-style; author provides real repo context |

Payment timing: Upon SME Content Lead approval (typically 3–5 days after submission). Contractor invoices via Google Form → Razorpay invoice link (auto-generated).

### Reviewer Pool Inverted-Bonus Model (unique to QOrium)

Hypothesis: More SMEs reviewing the same question = higher quality feedback + faster validation cycle. Standard model is “one SME reviews”; we invert to “pool of 3–5 SMEs review, highest-quality feedback wins.”

Mechanic: - When a question goes to “SME Review” stage (Stage 4 of Content Engine), it’s sent to a pool of 3 related-domain SMEs - Each SME submits feedback independently (don’t see each other’s reviews) - I/O Psych contractor synthesizes feedback + merges decisions - Bonus pool: Of the per-question budget, allocate 10% as “reviewer pool bonus.” Divide equally among SMEs whose feedback materially changed the question (cited >2 times in final revision)

Example: Coding question budgeted at ₹1,500. Primary author gets ₹1,500. If 3 reviewers provide feedback, 10% bonus pool (₹150) is split: Reviewer A gets ₹75 (feedback used 3x), Reviewer B gets ₹50 (used 2x), Reviewer C gets ₹25 (used 1x). Authors + reviewers all earn more.

Benefit: Contractors want to review (earn bonus). Better-quality reviews accelerate validation. Scales the SME network without exploding headcount.

Cost envelope: Reviewer pool bonus adds ~5–8% to content production cost (₹500–₹750 per question) but accelerates M2–M4 ramp significantly.

## 6. Outreach Email Templates (3 variants)

### Template 1: Talpro Alumni Warm

Subject: QOrium — Talpro’s new venture. You’d be perfect.

Hi [Name],

Quick note — Bhaskar’s started QOrium at Talpro Universe, a question bank for hiring assessments. You remember how staffing is all about signal quality? QOrium fixes the leaked-test problem.

We’re building a network of senior [domain] engineers to review AI-drafted questions — ₹500–₹2,000 per question, 5–10 hours/month to start, pure remote.

You’d be reviewing questions in [specific domain you’re expert in]. Your call would land with customers like Bosch, JPMC India, large staffing firms within weeks.

Interested in a 15-min Zoom this week?

[Link to apply]

Cheers,
[Your name]
QOrium · A Talpro Universe venture

### Template 2: Cold LinkedIn / Hashnode

Subject: Opportunity — Technical question authoring ($2,000+ per article)

Hi [Name],

Saw your [blog post / LinkedIn post / GitHub repo] on [specific technical topic]. Excellent depth.

We’re QOrium, building the world’s question bank for hiring assessments. We pay senior engineers ₹1,500–₹2,500 per validated question to author + review assessment content in their specialty. 5–10 hours/month, fully remote.

Your expertise in [domain] is exactly what we need. If interested, 15-min call?

[Link to vetting signup]

Cheers

### Template 3: Referral Intro

Subject: Referral bonus opportunity — bring a senior engineer

Hi [Existing SME Name],

You’ve done great work on questions [dates/topic]. We want to scale our SME network.

Know a senior [domain] engineer who’d review questions like you do? We pay ₹15,000 referral bonus when they complete vetting + 5 pilot questions. You both earn.

[Referral link]

Spread the word!

Cheers

## 7. Tracking Spreadsheet Seed

Central tracker (Google Sheets) to monitor all 250+ contractors. Replicate this schema:

| Column | Type | Purpose |
| --- | --- | --- |
| Name | Text | Contractor name |
| Domain | Dropdown | Primary expertise (Java, React, SAP ABAP, etc.) |
| Email | Email | Primary contact |
| WhatsApp | Phone | For quick coordination |
| Source | Dropdown | How we found them (Talpro alumni, NIT network, Topmate, LinkedIn, Referral, etc.) |
| Status | Dropdown | Sourced / Vetting gate 1 / Gate 2 / Gate 3 / Gate 4 (pilot) / Certified / Inactive / Churned |
| Vetted Date | Date | When they passed gate 4 |
| Batches Completed | Number | # of paid batches they’ve authored |
| Quality Score (avg) | Number | 0–100; aggregated from gate 4 + subsequent batches |
| Total ₹ Paid to Date | Currency | Cumulative earnings |
| Last Active | Date | Last batch submitted or reviewed |
| Notes | Text | Feedback, strengths, specialties, known issues |
| Churn Risk | Dropdown | Green / Yellow / Red (based on: inactivity >30 days = yellow, >60 days = red) |

Monthly metrics rolled up from tracker:

- Total contractors (filtered by Status = “Certified”)

- Monthly batch throughput (sum of “Batches Completed” last 30 days)

- Average cost per validated question (Total ₹ Paid / Questions delivered)

- Churn rate (Churned / Total in month)

- Quality (% of batches passing gate with 4/5+ questions)

## 8. Risks (3 major risks + mitigation)

### Risk 1: Contractor Flake Rate

Description: Contractors pass vetting, get certified, then submit low-quality first batch or ghost after gate 4.

Probability: Medium (likely 30–50% of certified contractors become inactive in M1–M2).

Mitigation: - Gate 4 pilot batch is the real test; pay only on approval (no upfront cost) - Monthly check-in email from SME Content Lead to inactive contractors (>7 days without submission) asking for status - Implement “cold start” logic: if a contractor is inactive >30 days, remove them from auto-invite queue; require re-engagement conversation to reactivate - Offer “batch credits” (prepay ₹5,000 for 5 questions to ensure commitment)

### Risk 2: Quality Variance Bottleneck at SME Lead

Description: 100+ contractors creating questions, but SME Content Lead is the bottleneck for gate 4 review. Turnaround > 2 weeks → contractor frustration → churn.

Probability: High (single-person bottleneck is classic scaling failure).

Mitigation: - Hire Content Ops Manager (hire #7, M7) whose ONLY job is contractor QA + batch review - Implement async batch review: instead of SME Lead reviewing every question, use I/O Psych contractor (hire #5, M4) for statistical sampling + rubric-based gate 4 scoring - Reviewer pool inverted-bonus model (section 5) → delegate review load to certified contractors themselves - Establish SLA: gate 4 feedback within 5 days of submission (enforced by calendar blocks)

### Risk 3: IP + Confidentiality Breach via Contractor

Description: Contractor leaks customer-specific questions (e.g., Bosch Stack-Vault questions) or publishes QOrium proprietary content on GitHub.

Probability: Low, but high impact.

Mitigation: - All contractors sign MSA (A6 standard, drafted by legal counsel by M1) covering: - IP assignment (all questions are QOrium IP) - Confidentiality + non-disclosure (1-year post-engagement) - Non-compete (cannot author assessment content for competitors for 1 year) - Clawback clause (if leaked, contractor is liable for damages) - GitHub scan: weekly check of public repos for leaked questions (via Serper.dev + text search) - Watermark all Stack-Vault questions shared with contractors (so leaks are attributable) - Contractor onboarding includes 1-page “IP Policy” summary — acknowledge in email before first batch

## 9. Tracking Spreadsheet Link + Data Governance

Primary source of truth: QOrium-SME-Contractor-Network.xlsx (stored in Talpro Universe shared drive).

Access: SME Content Lead (hire #2) + Content Ops Manager (hire #7) + CEO (read-only). Read-only for CTO (quarterly snapshot).

Monthly sync: Content Ops Manager updates tracker by 5th of each month. CEO + CTO review in weekly Monday pipeline meeting.

Archival: Historical data (completed contractors) migrated to SME-Network-Archive.xlsx annually.

## 10. Onboarding Sequence (once contractor is certified, before first paid batch)

- Email: NDA + MSA — Contractor reviews, e-signs via DocuSign

- Email: Zoom link to kick-off call (30 min with SME Content Lead)

  - Walk through actual sample questions + quality rubric

  - Assign first batch (5–10 questions)

  - Set deadline (2 weeks)

  - Confirm payment method (Razorpay invoice)

- Sandbox access: Google Doc + Notion template + Reference questions

- Slack channel add: Private QOrium-SMEs workspace (async questions, issue escalation)

- First batch submission → review → approval → payment

End of C6 — SME Contractor Sourcing Plan v1.0. Next: B1 VPS Capacity and Topology Plan.