# QOrium Launch Communications Plan

Author: CMO / Head of Marketing, Talpro Universe
Audience: Executive team, marketing team, Talpro India leadership
Date: May 1, 2026
Status: v1.0 — Finalized launch strategy across 3 phases
Companion docs: Blueprint v1.1, Customer-Success-Playbook

## Executive Summary

QOrium launches in three phases over 12 weeks:

- Stealth Phase (Weeks 1–3): Customer Zero validation, internal alignment, soft launch to Talpro network.

- Soft Launch (Weeks 4–6): Controlled rollout to Bosch & Biz4Tech, case studies, thought leadership.

- Public Launch (Weeks 7–12): Public website, press, community activation, product hunt launch.

Success metrics: 10+ customers by Month 3 end, 50+ revenue-generating transactions, 1,000+ community members, 5+ pieces of published thought leadership.

## Table of Contents

- Phase 1: Stealth (Weeks 1–3)

- Phase 2: Soft Launch (Weeks 4–6)

- Phase 3: Public Launch (Weeks 7–12)

- Internal Communications

- Customer Zero Communications

- Cross-Product Positioning

- Crisis Communications Playbook

- Launch Measurement Dashboard

## Phase 1: Stealth (Weeks 1–3)

Objective: Validate product-market fit with Customer Zero (Talpro India), de-risk launch, build internal consensus.

### 1.1 Week 1: Internal Kickoff

Audience: Talpro Universe leadership, QOrium core team
Format: In-person + async Slack

Deliverables:

- Internal Memo (Day 1): CEO announces QOrium to Talpro Universe team via all-hands + memo. Tone: “We’re solving a $2B+ problem in technical recruiting. Here’s our edge.”

- Team Kickoff (Day 2): 90-minute in-person session with exec team + CMO + VP Sales + VP Product. Align on 3-month roadmap, message pillars, GTM risks.

- Sales Enablement Deck (Day 3): 15-slide internal deck covering 3 SKUs, unit economics, target personas, objection handling.

- Slack #qorium-launch channel (Day 1): Async updates, resource links, wins celebration.

Key Messages for Internal Team: - QOrium is a B2B2B SaaS venture: we license question banks to platforms, staffing platforms, and enterprises. - 3 SKUs: ReadyBank (shared commodity), JD-Forge (on-demand custom), Stack-Vault (exclusive IP). - Moat: anti-leak engine (daily crawl + semantic similarity) rotates compromised questions 3–7 days. - Year 1 revenue target: ₹3.5Cr ARR ($420K).

### 1.2 Week 2: Customer Zero (Talpro India) Validation

Audience: Talpro India CEO, Operations Head, Hiring Team
Format: In-person + Slack

Deliverables:

- Executive Briefing (Day 1): CMO + VP Sales + CTO present to Talpro India leadership. Walk through product, roadmap, Customer Zero expectations.

- Product Demo (Day 2): Full walkthrough of ReadyBank + JD-Forge with live data. Show anti-leak dashboard. Gather feedback on feature gaps.

- Onboarding Playbook (Day 3–5): Hand-hold Talpro India through API setup, first 50 question imports, first JD-Forge order. Document all friction points.

- Internal Case Study Draft: Capture Talpro India’s hiring volume, question library size, pain points. Frame as “how we reduce leak risk by 90% vs. public question banks.”

Success Criteria (Week 2): - Talpro India team can execute full workflow independently. - Identified 5+ feature requests or UX fixes; prioritize for Month 1. - Customer Zero NPS ≥ 7 on initial experience. - Product feedback validated hypothesis: anti-leak engine + JD alignment > existing solutions.

### 1.3 Week 3: Soft Outreach to Target Customers

Audience: Bosch, Biz4Tech, Recruiter Network
Format: Email + personal calls

Deliverables:

- Outreach Email (Day 1): Personalized email to Bosch VP Talent + Biz4Tech CEO + 3–5 key recruiters. Subject: “New Question-Bank Solution Built for Technical Hiring.” Tone: exclusive early-access offer, invite to 30-min demo.

- Demo Scheduling (Day 2–5): Schedule 3–5 initial discovery calls. Goals: validate pain point (question leakage, time-to-market), understand current workflow, identify objections.

- Bosch Deep-Dive (Day 3): If positive signal, schedule 60-minute working session with Bosch hiring manager + tech lead. Walk through their hiring workflow, show JD-Forge capability.

- NDA Preparation (Day 5): For any customer showing strong intent, prepare lightweight NDA for Stealth phase feedback.

Key Message (Outreach): “We’ve built QOrium — a question bank platform with an anti-leak engine that auto-rotates compromised questions. 10+ of your questions are on Reddit/GitHub right now; we catch & replace them in <7 days. Early adopters get 50% discount on Year 1 ARR + exclusive feature input.”

Success Criteria (Week 3): - 3–5 customer discovery calls scheduled. - 1 customer (Bosch or Biz4Tech) signals serious intent to pilot. - Talpro India Customer Zero is live on ReadyBank, beginning to generate data.

## Phase 2: Soft Launch (Weeks 4–6)

Objective: Close 2–3 pilot customers, generate case study momentum, build proof points for public launch.

### 2.1 Week 4: Bosch & Biz4Tech Onboarding

Audience: Bosch hiring team, Biz4Tech ops team
Format: Hands-on + Slack

Deliverables:

- Week 4 Kickoff: Formal onboarding call with customer sponsor + technical team. Walk through API setup, admin console, expected timelines.

- ReadyBank Integration: Help customer load their question export into ReadyBank (or begin searching commodity library). Track: # questions imported, # searches per day.

- First JD-Forge Order: Execute first custom question order. For Bosch: 50-question set for “Senior Backend Engineer, Java + Microservices.” For Biz4Tech: 20-question set for “Full Stack Engineer.”

- Feedback Loop: Weekly 30-min sync with customer to gather product feedback, identify blockers, celebrate wins.

Measurement (Week 4 End): - Bosch: 2,000+ questions in ReadyBank, 5+ JD-Forge orders submitted, first feedback submitted. - Biz4Tech: 500+ questions, 3+ JD-Forge orders, positive NPS score. - Talpro India: 10,000+ question searches, 50+ JD-Forge orders, 0 leaked questions detected.

### 2.2 Week 5: Case Study Production

Audience: Marketing team, potential customers (for future promotion)
Format: Written + video

Deliverables:

- Talpro India Case Study (Draft): 1,500-word written case study. Sections:

  - Problem: Hiring at scale with 3,000+ engineers; 10% of interview questions leak to public forums.

  - Solution: QOrium ReadyBank (commodity) + JD-Forge (on-demand). Anti-leak engine catches leaks in <7 days.

  - Results: 90% leak risk reduction, time-to-market for custom questions: 30 days → 2 hours, hiring velocity +25%.

  - ROI: Prevented 500+ compromised assessments (at ₹5,000/leak cost = ₹25L impact).

  - Quotes: Talpro India CEO on “why we dogfood everything we build” + Hiring Manager on “can finally trust our question bank.”

- Bosch Case Study (Light Version): 800-word summary. Problem: Managing 200+ hiring managers across regions. Solution: JD-Forge + API integration. Results: time-to-market -80%, consistency across regions +50%.

- Testimonial Video (Optional): 3-minute recorded testimonial from Talpro India CTO or Hiring Manager. Talk through pain point, product demo, ROI. Use for future product hunt, landing page.

Deliverable Quality: High-polish; review by CMO + CEO. Include data (metrics), quotes, & visuals (screenshots).

### 2.3 Week 6: Thought Leadership Prep

Audience: Engineering leaders, recruiting leaders, technical community
Format: Blog, LinkedIn, webinar

Deliverables:

- Blog Post 1: “The Question Leakage Epidemic” (1,500 words)

  - Thesis: 60% of popular tech interview questions are available on public forums. Companies that use them are unknowingly testing question memorization, not true capability.

  - Data: cite Reddit threads, GitHub repos, LeetCode overlap data. Reference Talpro India data point (anonymized): 10% leak rate.

  - Solution hint: auto-rotation + semantic leak detection (don’t name QOrium yet, tease it).

  - CTA: “Join us for an exclusive webinar on May 22 where we’ll reveal how we solved this.”

  - Publish on: Talpro blog + Medium + LinkedIn.

- LinkedIn Article by CEO (1,000 words)

  - Title: “Why We Built QOrium: A Venture in Question Quality”

  - Narrative: Talpro’s journey across 4 products. Hiring is the hardest problem. Now building the hiring question layer. Vision: become the standard question provider for global technical hiring.

  - Tone: aspirational, founder POV, not salesy.

- Webinar Plan (June 2): “How to Stop Leaking Your Interview Questions” (live panel with Talpro India Hiring Manager + independent recruiter). 500+ registrations target.

Success Criteria (Week 6): - Talpro India case study in final review (publish Week 7). - Blog post published; 500+ organic views in first week. - LinkedIn article garners 50+ comments, 1,000+ impressions. - Webinar registrations: 200+ by Week 6 end.

## Phase 3: Public Launch (Weeks 7–12)

Objective: Go public, acquire 10+ customers, hit $50K MRR, establish market presence.

### 3.1 Week 7: Public Website & Brand Launch

Audience: General market, recruiters, hiring leaders
Format: Public website, email, social media

Deliverables:

- Marketing Website (qorium.io):

  - Hero: “Your question bank shouldn’t leak. QOrium’s anti-leak engine rotates compromised questions in <7 days.”

  - 3 product tiles (ReadyBank, JD-Forge, Stack-Vault) with pricing, features, example use cases.

  - Talpro India case study (published + featured).

  - Pricing page: transparent SKU pricing, tier comparison, ROI calculator.

  - Team page: founder + CMO + key hires with bios.

  - Blog: 3 published articles + ongoing cadence (1/week).

  - FAQ: 20+ common questions (pricing, integrations, compliance, anti-leak details).

  - Demo video: 3-min product walkthrough.

  - CTA: “Start Free Trial” (7-day ReadyBank access) + “Schedule Demo” (for JD-Forge/Stack-Vault).

- Email Launch Campaign (Day 1):

  - Segment 1 (Existing warm leads): Bosch, Biz4Tech, Talpro network. Subject: “QOrium is now live — your early-access guide.” Highlight: pilot customer pricing + exclusive features.

  - Segment 2 (Recruiter network): 200+ recruiters from Talpro’s database. Subject: “Stop using the same questions everyone else is using.” Tone: problem-focused.

  - Segment 3 (Broader market): Growth marketing email list. Subject: “Save 80% time on interview question creation.”

- Social Media Launch:

  - LinkedIn: 3 posts over Week 7 (CEO announcement, product launch, case study feature). Paid promotion: $5,000 budget, target: “VP Talent,” “Director of Recruiting,” “CTO,” geographic: India + US.

  - Twitter/X: Live-thread on launch day. Technical audience. Tag: @anthropic, @talpro_universe, @ylcombinator (if YC-backed signaling).

- Press Release: Distribute via PRWeb + India press channels. Headline: “QOrium Launches Question-Bank SaaS with Anti-Leak Engine; Solves $2B+ Problem in Technical Hiring.”

Success Criteria (Week 7): - Website live, all pages tested & fast-loading. - Email campaign: 30% open rate, 5% click-through, 2+ demo requests. - LinkedIn posts: 500+ impressions, 20+ comments. - Case study published on website + referenced in press. - 10+ inbound demo requests by Week 7 end.

### 3.2 Week 8–9: Sales Sprint & Acquisition

Audience: Target customers (Bosch, Biz4Tech, recruiters, enterprises)
Format: Sales calls, demos, enterprise negotiations

Deliverables:

- Sales Playbook Execution: VP Sales leads sprint to close 5+ pilot customers (by Week 9 end). Target: 2 enterprise (Bosch-type), 3 platform/recruiter (Biz4Tech-type).

- Demo Content: 30-min + 60-min demo decks. Customize per customer segment (enterprise vs. recruiter vs. platform).

- Pricing Negotiation: Flexible Year 1 pricing for early adopters (10–20% discount for public customer references).

- Legal/Contracts: Pre-negotiated SLA & MSA templates (reviewed by legal; turnaround: 5 business days).

Measurement (Week 9): - Closed deals: 5+ signed contracts. - ARR added: $100K+ (from new + Customer Zero + Bosch/Biz4Tech upgrades). - Pipeline: 20+ qualified opportunities.

### 3.3 Week 10: Product Hunt Launch

Audience: Tech community, indie hackers, developers
Format: Product Hunt + Twitter + community forums

Deliverables:

- Product Hunt Preparation (Week 9–10):

  - Finalize product hunt listing (tagline, description, visuals, 3-min demo video).

  - Prepare social media push: 100+ Slack workspaces (indie hacker + hiring communities) for launch day promotion.

  - Coordinate with 3–5 micro-influencers in recruiting tech space (DM: “We’d love your feedback on QOrium”; send early access).

  - Prepare response playbook: 50+ likely questions + answers for product hunt comments.

- Launch Day (Week 10):

  - Live Product Hunt launch at 12:01 AM PT (9:30 AM IST).

  - CEO active in comments for first 6 hours (answer questions, engage community).

  - Twitter thread live simultaneously (thread covering: problem, solution, 3 SKUs, example use case, roadmap).

  - Paid promotion: $2,000 across Product Hunt + Twitter + Reddit.

Target Metrics (Week 10): - Product Hunt: Top 10 ranking, 500+ upvotes, 100+ comments. - Website traffic: 5,000+ visitors from PH. - 50+ new trial signups. - Twitter: 50,000+ impressions, 500+ engagements.

### 3.4 Week 11–12: Content & Community Momentum

Audience: Technical hiring leaders, engineering communities
Format: Webinars, blog, Twitter Spaces, community forums

Deliverables:

- Webinar Series (Week 11): “How to Stop Leaking Your Interview Questions” (live, June 2, 2 PM IST).

  - Panels: Talpro India Hiring Manager + independent recruiter + QOrium CEO.

  - Promotion: email, LinkedIn, Twitter, Product Hunt, Hacker News. Target: 500+ registrations.

  - Recording: publish to YouTube, embed on website.

- Blog Content (Weeks 11–12): Publish 2 more high-impact articles:

  - “Interview Question Leakage: A Data-Driven Analysis of Reddit, GitHub, and LeetCode”

  - “How IRT Calibration Improves Question Quality (and Why Your Current Questions Probably Aren’t Calibrated)”

  - Organic SEO target: rank for “interview questions,” “technical assessment,” “hiring questions” (within 3 months).

- Twitter Spaces (Week 11): Host live Spaces discussion: “Is Your Interview Question Bank Leaking?” with industry experts. Promote to 10,000+ followers (via followers of CTO, CEO, VP Sales).

- Community Engagement:

  - r/recruiting, r/techhr, r/hiring: Share insights (not sales), participate in discussions, answer 20+ questions per week.

  - Hacker News: Post about anti-leak technology, engage in technical discussions.

- Month 1–3 Blog Roadmap (Finalize):

  - Week 7: “The Question Leakage Epidemic”

  - Week 8: “How to Evaluate Question Quality”

  - Week 10: “Anti-Leak Technology: How QOrium Detects Question Leakage”

  - Week 11: “Interview Question Leakage: A Data-Driven Analysis”

  - Week 12: “How IRT Calibration Improves Question Quality”

  - Week 13: “Building the World’s Best Technical Question Bank”

Success Criteria (Weeks 11–12): - Webinar: 500+ registrations, 250+ attendees, NPS ≥ 8. - Blog posts: 2,000+ organic views per post, 20+ backlinks. - Twitter Spaces: 1,000+ listeners, 50+ follow-ons from spaces. - Community: 1,000+ members across Reddit, Slack, Hacker News.

## Internal Communications

### Week 1: All-Hands Announcement

Format: Sync all-hands + recorded message (for async teams)

Key Talking Points: 1. “QOrium solves a $2B+ TAM problem: question leakage in technical hiring.” 2. “We have a defensible moat: anti-leak engine with 7-stage content pipeline.” 3. “Customer Zero is Talpro India — we dogfood everything we build.” 4. “3 SKUs address different buyer types: platforms, enterprises, recruiters.” 5. “Year 1 revenue target: ₹3.5Cr ARR. Year 2: ₹12Cr. Year 5: ₹500Cr+.”

Deliverable: Recorded 10-min message from CEO + async Slack FAQ channel.

### Ongoing: Weekly Launch Updates

Format: Slack #qorium-launch channel + weekly email

Cadence: Every Friday 4 PM IST

Content: - Customer wins (anonymized if needed) - Metrics update (trials, signups, demos booked, revenue) - Upcoming milestones - Risks & mitigations - Shout-outs for great work

## Customer Zero Communications

### May 1–3: Discovery Phase

Audience: Talpro India CEO, VP Operations, Hiring Head
Format: In-person + slides

Deliverable: 60-minute working session. Agenda: 1. Product demo (ReadyBank, JD-Forge, Anti-Leak Dashboard) 2. API walkthrough (show integration points) 3. Timeline: when can we onboard 100+ questions from Talpro India into ReadyBank? 4. First JD-Forge order: can we generate 50 questions for “Senior Backend Engineer” role? 5. Feedback: what features would unlock 10x value for Talpro India?

### May 4–10: Onboarding Phase

Audience: Talpro India operations team
Format: Hands-on + Slack

Deliverables: - API key provisioning & setup guide - Bulk question import workflow (CSV → PostgreSQL) - First ReadyBank searches (demonstrate search, export) - First JD-Forge order submission (capture hiring manager feedback) - Dashboard walkthrough (API usage, anti-leak alerts, quality metrics)

### May 11–31: Usage & Feedback Phase

Audience: Talpro India hiring managers + ops team
Format: Weekly 30-min sync + Slack

Metrics Tracked: - # questions imported to ReadyBank - # ReadyBank searches per week - # JD-Forge orders submitted - # questions released (Post-SME review) - # leak alerts triggered - NPS & qualitative feedback

Goal: Demonstrate 100+ questions imported, 10+ JD-Forge orders, 0 false leak alerts, NPS ≥ 8 by Month 1 end.

## Cross-Product Positioning

### How QOrium Fits the Talpro Universe Ecosystem

Messaging (Internal + Customer):

“QOrium is the question-bank layer of the Talpro hiring platform. Just as LeadHunter qualifies candidates and HireIQ vets engineers, QOrium ensures the questions themselves are high-quality, leak-resistant, and calibrated to your role requirements.”

Product Bundling (Future): - LeadHunter → QOrium: Qualified leads take QOrium assessments. - QOrium → HireIQ: Question performance data feeds HireIQ’s candidate scoring. - HireIQ → ProveIQ: Interview results integrated into ProveIQ skill graph.

Messaging for Salesforce: “Upsell QOrium to existing LeadHunter + HireIQ customers. Value prop: reduce hiring risk, faster time-to-offer, defensible question bank.”

Messaging for Marketing: “Position QOrium as ‘the question bank for companies that can’t afford leaks.’ Contrast with LeetCode (public, leaked), HackerRank (no anti-leak), internal libraries (no AI).”

## Crisis Communications Playbook

### Scenario 1: Product Security Incident (Question Leak Not Caught)

Detection: Customer reports question on Reddit that should’ve been caught by anti-leak engine.

Response (within 4 hours): 1. Triage: confirm leak is real, determine customer impact, assess severity (1–5 scale). 2. CEO + CTO + CMO emergency standup (30 min). 3. Internal Slack #incident: post status update, impact statement, remediation plan. 4. Direct customer outreach: CMO calls customer sponsor, explains root cause, offers remediation (question rotation + credit). 5. Post-mortem: schedule 48-hour post-incident review.

Public Messaging (if leaked): “We detected a question leak faster than our SLA. This is exactly why we built QOrium’s anti-leak engine. We’ve automatically rotated the question and offered our customer a credit. Learn more: [blog post].”

Tone: Transparent, problem-solving, not defensive.

### Scenario 2: False Leak Alert (Question Flagged as Leaked But Isn’t)

Detection: Customer reports false positive on anti-leak alert.

Response (within 2 hours): 1. Investigate: confirm it’s a false positive, determine cause (e.g., semantic model too aggressive). 2. Mark as false positive in system (train model with feedback). 3. Customer outreach: apologize, explain cause, offer action (improve model). 4. Public messaging (if disclosed): “We’re improving our model to reduce false positives while maintaining leak detection accuracy.”

Tone: Apologetic, learning-oriented.

### Scenario 3: Major Customer Churn (e.g., Bosch Exits)

Detection: Customer requests early exit / non-renewal signals.

Response (same day): 1. CMO + VP Sales immediately engage: discovery call to understand pain points (is it product, price, integrations, support?). 2. Escalation: if escalation is needed, CMO briefs CEO; consider executive intervention. 3. Remediation: offer service credit, expedite roadmap feature, assign dedicated success manager. 4. Internal comms: don’t publicize; track in dashboard.

Messaging (if public): Only if customer volunteers to share reason. Otherwise, no comment.

### Scenario 4: Negative Press / Industry Criticism

Detection: Article questioning QOrium’s anti-leak effectiveness, or questioning market demand.

Response (within 24 hours): 1. Assess: is the criticism valid? Is it based on outdated info or misunderstanding? 2. Data response: prepare blog post or LinkedIn article with data refutation (cite examples, metrics, case studies). 3. CEO engagement: CEO considers direct response (thoughtful, non-defensive) or amplification of data response. 4. Internal: brief team, don’t amplify criticism internally.

Tone: Data-driven, not emotional.

## Launch Measurement Dashboard

Track these metrics weekly throughout launch (Weeks 1–12):

| Metric | Phase 1 Target | Phase 2 Target | Phase 3 Target | How to Measure |
| --- | --- | --- | --- | --- |
| Customers | 1 (Talpro India) | 3 (+ 2 pilots) | 10+ | Sales CRM, signed contracts |
| ARR | ₹5L | ₹15L | ₹50L+ | Revenue dashboard |
| MRR Recurring | ₹30K | ₹100K | ₹400K+ | Stripe/invoicing system |
| Trials Signup | 5 | 25 | 200+ | Trial signup form |
| Demo Requests | 3 | 10 | 50+ | Calendar system |
| Case Studies Published | 0 | 1 (Talpro India) | 2 (+ Bosch) | Blog/website |
| Blog Views | 0 | 1,000 | 10,000+ | Google Analytics |
| LinkedIn Followers | 100 | 500 | 2,000+ | LinkedIn analytics |
| Twitter/X Followers | 100 | 500 | 2,000+ | Twitter analytics |
| Webinar Registrations | 0 | 200 | 500+ | Eventbrite |
| Community Members | 0 | 100 | 1,000+ | Slack, Reddit, HN |
| NPS (Customer) | 7+ | 8+ | 8+ | Surveys, interviews |
| Website Traffic | 100/day | 500/day | 5,000+/day | Google Analytics |
| Press Mentions | 0 | 2–3 | 5+ | Google Alerts, PRWeb |

Review Cadence: Weekly CMO review; monthly exec review (CEO, CFO, CMO, VP Sales).

Dashboard Owner: Head of Marketing (CMO). Access: CEO, CFO, VP Sales, VP Product.

Red Flags (Immediate Escalation): - No new customers by Week 6 end. - Case study completion >1 week late. - Website traffic flat week-over-week in Weeks 9–12. - NPS <6 from Customer Zero or any paying customer. - Major press criticism unanswered for >48 hours.

## Content Channels & Cadence Summary

| Channel | Frequency | Owner | Target Audience |
| --- | --- | --- | --- |
| Blog (qorium.io) | 1/week (Weeks 7+) | CMO/Content Manager | Hiring leaders, technical community |
| LinkedIn (Corporate) | 3x/week | CMO | B2B recruiting, hiring leaders |
| LinkedIn (CEO Personal) | 2x/week | CEO | General startup community |
| Twitter/X | 3–5x/week | CMO/Growth | Technical community, VCs, influencers |
| Email (Customer Newsletter) | 2x/month (post-launch) | CMO | Existing customers, free trials |
| Email (Sales Sequences) | Triggered | VP Sales | Prospects in pipeline |
| Webinars | Monthly (Weeks 10+) | CMO/VP Sales | Hiring leaders, recruiters |
| Slack (Communities) | Daily (organic) | Growth/CMO | Indie hackers, hiring communities |
| Reddit/Hacker News | 3x/week (organic) | CMO/Growth | Technical community |
| Twitter Spaces | Bi-weekly (Weeks 11+) | CEO/CMO | Community discussion, audience building |

Launch Owner: CMO (with CEO oversight). Escalation point for any red-flag metrics or crises: CEO + CFO.